## Sheet1
Project Name: | APEX
Project Start: | 2025-02-24
End Project: | 2025-05-09
weeks in progress: | 11
[6 empty] | 2025-02-24 | 2025-03-03 | 2025-03-10 | 2025-03-17 | 2025-03-24 | 2025-03-31 | 2025-04-07 | 2025-04-14 | 2025-04-21 | 2025-04-28 | 2025-05-05
phase | Tasks | Responsible Person | Start Date | End Date | Days | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
Project Planning & Management
| Define the project idea | Nouran | 2025-02-24 | 2025-02-27 | 3
| create a Gantt Chart | Dalia | 2025-02-27 | 2025-03-01 | 2
Literature Review
| Research related literature | mohamed | 2025-03-01 | 2025-03-03 | 2
| review similar projects | mohamed | 2025-03-04 | 2025-03-05 | 1
Requirements Gathering
| Collect project requirements | Joseph | 2025-02-24 | 2025-02-27 | 3
| define objectives | Joseph | 2025-02-25 | 2025-02-28 | 3
System Analysis & Design
| Create sketches | Salma | 2025-02-25 | 2025-03-01 | 4
| select colors and typography | Mostafa | 2025-02-26 | 2025-03-02 | 4
Implementation
| Develop the design using Photoshop, Illustrator, and InDesign | All Team | 2025-03-24 | 2025-05-01 | 38
Final Presentation & Testing & Reports
| Review the project, prepare the final presentation, write reports | All Team | 2025-05-01 | 2025-05-09 | 8
0